Green PFM II — Rwanda Feasibility Study

Disbursement-Linked Indicator Matrix

Kigali Field Mission — May 2026  |  Draft for internal review

Overview

| Preferred | DLI | Title | Tier | Type | Year |
| --- | --- | --- | --- | --- | --- |
| Y | A1.1 | Integration of climate risks in the macroeconomic framework | Immediate | Process Reform | Year 1 |
| N | A1.2 | Climate-augmented macroeconomic forecasting | Immediate | Process Reform | Year 2–3 |
| Y | A1.3 | Greening of monetary policy instruments — feasibility study | Secondary | Strategy & Framework | Year 2–3 |
| N | A2.1 | Corporate sustainability diagnostic and NZCB roadmap | Immediate | Strategy & Framework | Year 1 (prerequisite) |
| Y | A2.2 | Carbon footprint of BNR reserves and green Investment Policy | Secondary | Process Reform | Year 1–2 |
| N | B1.1 | Sovereign SLL issuance includes a climate-related KPI | Immediate | Market Activation | Year 1–2 |
| Y | B1.2 | National deforestation monitoring as climate finance data infrastructure | Immediate | Data Infrastructure | Year 2–3 |
| N | B1.3 | Forestry-anchored SLF framework and first issuance | Immediate | Strategy & Framework | Year 3 |
| Y | B2.1 | Regulatory framework for climate insurance distribution via SACCOs | Immediate | Strategy & Framework | Year 1 (prerequisite) |
| N | B2.2 | Rwandan insurer pool for climate risk underwriting | Secondary | Market Activation | Year 2–3 |
| N | B2.3 | First parametric climate insurance product in active distribution | Secondary | Market Activation | Year 3 |
| Y | B3.1 | CMA green product certification mechanism and sustainability function | Immediate | Strategy & Framework | Year 1–2 |
| N | B3.2 | ESG Data Hub — RSE Green Exchange Window uptake | Immediate | Data Infrastructure | Year 1–2 |

Axis A — Greening of Central Banking

General objective:  BNR has developed a strategy and tools to contribute to the greening of Rwanda's financial system in line with the country's climate commitments.

A1 — Monetary Policy

Sub-objective:  Climate risks are integrated in BNR's monetary policy decision-making process and reflected in the operational macroeconomic framework.

The three DLIs under this sub-axis build sequentially from research/analysis to operations. A1.1 formalises what already happens informally (climate/weather variables enter MPC discussions) by anchoring them in published research and a concept note integrated into the MPC briefing cycle. A1.2 extends the forecasting horizon using satellite imagery and ESTEEM model outputs (to be confirmed with ESTEEM team). A1.3, the feasibility study for greening monetary instruments, is the most ambitious and politically sensitive and classified as a secondary strategic ambition.

| ▸ Process Reform |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| A1.1 | Integration of climate risks in the macroeconomic framework |  |
| Institution(s): BNR — Monetary Policy Department |  | Year: Year 1 |  |

DLI DESCRIPTION

BNR publishes a research paper and concept note on climate channels in the Rwandan macro framework, formally integrated into the MPC briefing cycle.

RATIONALE

Climate variables (rainfall patterns in particular) already enter MPC discussions informally, and the November 2025 MPC explicitly flagged a climate-negative scenario that materialised. However, no formal published research exists on climate transmission channels in Rwanda's macro framework. Formalising this through a published paper and concept note creates the analytical foundation for A1.2 and A1.3, and positions BNR to meet its NGFS co-chairmanship expectations.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Workshop on climate macro transmission channels for MPC research team | 5 |
| Peer exchange with climate-active central bank (e.g. BdF) and research institutions | 10 |
| Co-authoring support for BNR Review paper | 20 |
| QPM climate scenario integration methodology | 20 |
| Total indicative TA | 55 |

FEASIBILITY SCORING

| Legal mandate | 4 / 4 |
| --- | --- |
| Policy alignment | 3 / 4 |
| Donor complementarity | 3 / 4 |
| Institutional ownership | 2 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Concept note drafted; team formed; first paper outline approved. | Paper co-authored and submitted to BNR Review; preliminary climate scenarios in MPC briefing. | Paper published; climate scenarios formally integrated into QPM documentation. |

KEY RISKS

Limited internal modelling capacity at BNR

Dependence on meteorological agency data quality

Sequencing with A1.2 and A1.3

| ▸ Process Reform |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| A1.2 | Climate-augmented macroeconomic forecasting |  |
| Institution(s): BNR — Monetary Policy Department; BNR — Data Science Team |  | Year: Year 2–3 |  |

DLI DESCRIPTION

BNR extends its forecasting horizon for weather-sensitive variables by integrating satellite imagery and ESTEEM model outputs into the QPM, with climate scenarios used in MPC forward guidance.

RATIONALE

BNR's current model is capped at a one-month horizon due to meteorological agency limitations; the data science team already uses satellite imagery for agricultural estimates. Adding a medium-term climate horizon would improve MPC forward guidance. AFD's ESTEEM mission (June 2026, floods/landslides) can provide a good starting point to refine this DLI which bridges a tangible data gap and builds directly on A1.1.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Satellite data pipeline scoping and architecture design | 10 |
| QPM extension modelling (ESTEEM integration) | 20 |
| Capacity building for BNR research and data science teams | 15 |
| Pilot module integration and documentation | 10 |
| Total indicative TA | 55 |

FEASIBILITY SCORING

| Legal mandate | 4 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 3 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Data architecture designed; satellite data pipeline scoped. | Pilot integration in one QPM module; capacity building for research division. | Full climate-augmented QPM with extended horizon operational; used in MPC briefing. |

KEY RISKS

Data availability and standardisation across agencies

Capacity bottlenecks in BNR research teams

Coordination with NEMA, NISR and Rwanda Meteorological Agency

| ▸ Strategy & Framework |  | SECONDARY |  |
| --- | --- | --- | --- |
| A1.3 | Greening of monetary policy instruments — feasibility study |  |
| Institution(s): BNR — Monetary Policy Department; BNR — Financial Stability |  | Year: Year 2–3 |  |

DLI DESCRIPTION

BNR conducts a feasibility study of climate-sensitive monetary policy tools (differentiated reserve requirements, green collateral adjustments), producing an internal concept note approved at Deputy Governor level.

RATIONALE

BNR is managing a live IMF-ECF reform (data-driven monetary policy framework, price-based auctions, exchange rate flexibility). Greening monetary instruments is the highest-profile axis internationally (NGFS co-chairmanship creates expectations) but remains untouched, for legitimate reasons. It is explicitly dependent on A1.1 and A1.2 as analytical prerequisites and is politically sensitive; a feasibility study is the appropriate first step.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Comparative international study on green monetary instruments | 10 |
| Political feasibility consultations with BNR departments | 5 |
| Feasibility study co-drafting and peer review | 10 |
| Internal concept note preparation for Deputy Governor | 5 |
| Total indicative TA | 30 |

FEASIBILITY SCORING

| Legal mandate | 2 / 4 |
| --- | --- |
| Policy alignment | 2 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 2 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Scoping note completed; political feasibility consultations underway. | Feasibility study drafted; internal concept note circulated. | Concept note approved at Deputy Governor level; pilot adoption scoped. |

KEY RISKS

High political sensitivity and interaction with live ECF reform

Statutory amendments potentially required

Sequencing dependency on A1.1 and A1.2

A2 — Net-Zero Central Banking

Sub-objective:  BNR has formalised its sustainability commitments and integrated climate criteria into its corporate governance and reserve management framework.

The two DLIs under this sub-axis address BNR's institutional positioning as a green central bank. A2.1 : the corporate sustainability diagnostic and NZCB roadmap is a direct and explicit request from the Strategy Directorate and represents the highest-priority immediate deliverable in the A-axis: it is the institutional precondition for the credibility of all other Axis A interventions. A2.2: the carbon footprint assessment of reserves and update of the Investment Policy has strong technical merit and resonates with the Financial Markets Directorate but might require Board approval, making it a less achievable.

| ▸ Strategy & Framework |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| A2.1 |  | Corporate sustainability diagnostic and NZCB roadmap |  |
| Institution(s): BNR — Strategy Directorate; BNR — Sustainability Steering Committee |  | Year: Year 1 (prerequisite) |  |

DLI DESCRIPTION

BNR completes a corporate sustainability diagnostic and publishes a Net-Zero Central Banking roadmap, validated by the Sustainability Steering Committee and timed to the July 2026 mid-term strategy review.

RATIONALE

The Strategy Directorate explicitly requested this diagnostic: sustainability initiatives are fragmented across BNR directorates with no coherent roadmap. The July mid-term strategy review is the natural timing hook. The Sustainability Report is on hold pending exactly this exercise. This DLI is the prerequisite for BNR's credibility as an NGFS co-chair and as a green financial regulator.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Corporate sustainability diagnostic (inventory of BNR initiatives) | 5 |
| NZCB roadmap co-drafting with Strategy Directorate | 15 |
| Steering Committee governance design and operationalisation | 5 |
| Sustainability Report framework design | 10 |
| Total indicative TA | 35 |

FEASIBILITY SCORING

| Legal mandate | 4 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Diagnostic completed; draft NZCB roadmap circulated for internal review. | Steering Committee operationalised; first Sustainability Report drafted. | Sustainability Report published; NZCB roadmap implementation in progress. |

KEY RISKS

Internal coordination capacity across BNR directorates

Timing alignment with July mid-term strategy review

Continuity risk if BNR leadership changes

| ▸ Process Reform |  | SECONDARY |  |
| --- | --- | --- | --- |
| A2.2 | Carbon footprint of BNR reserves and green Investment Policy |  |
| Institution(s): BNR — Financial Markets / Reserve Management; BNR — Board |  | Year: Year 1–2 |  |

DLI DESCRIPTION

BNR completes a carbon footprint assessment of its foreign reserves portfolio and updates its Investment Policy to integrate climate criteria, approved at Board level.

RATIONALE

The Financial Markets Directorate reacted positively to portfolio carbon footprinting. The exercise may prove that green bonds already form part of the portfolio. Discussions on green bonds as a reserve asset are already underway; the team is cautious but receptive. Board approval is the binding step and introduces uncertainty. AFD can leverage BdF/BIS peer exchange, which is BNR's explicit ask.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Carbon accounting methodology for reserves portfolio | 10 |
| Peer exchange with BdF / BIS experts on green reserve management | 10 |
| Investment Policy revision and climate criteria integration | 10 |
| Board presentation preparation | 5 |
| Total indicative TA | 35 |

FEASIBILITY SCORING

| Legal mandate | 3 / 4 |
| --- | --- |
| Policy alignment | 2 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 2 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Carbon accounting methodology agreed; baseline footprint completed. | Revised Investment Policy draft submitted to Board. | Board approval obtained; pilot green sovereign allocation implemented. |

KEY RISKS

Board approval uncertainty

Liquidity, safety, and return trade-offs with green assets

Data availability for issuer-level carbon scoring

Axis B — Green Financial Products and Markets

General objective:  Rwanda's financial system offers a diversified range of green financial products (sustainability-linked debt instruments, climate insurance, and capital market solutions) that channel private and public resources toward climate adaptation and mitigation.

B1 — Financial Instruments: Debt

Sub-objective:  Rwanda has issued a sovereign sustainability-linked financial (SLF) instrument backed by credible climate KPIs, supported by a national deforestation data infrastructure that enables multiple climate finance vehicles.

The three DLIs under this sub-axis form a deliberate sequence around sovereign sustainability-linked debt. B1.1 is the near-term anchor: AFD supports the review of the existing World Bank SLF framework to add a climate KPI and accompanies MINECOFIN through the issuance process ahead of the June 2027 target. B1.2 addresses the binding data constraint by building national deforestation monitoring capacity, creating a data public good that also serves carbon markets and REDD+. B1.3 builds on this data infrastructure to design a forestry-anchored SLF framework.

| ▸ Market Activation |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| B1.1 | Sovereign SLL issuance includes a climate-related KPI |  |
| Institution(s): MINECOFIN — DG Debt |  | Year: Year 1–2 |  |

DLI DESCRIPTION

The Government of Rwanda issues a Sustainability-Linked Loan or Bond that includes at least one KPI targeting climate adaptation or mitigation, with a defined SPT and independent third-party verification arrangement in place at issuance.

RATIONALE

The World Bank FCI advisory team is co-developing a SLF framework with MINECOFIN–DG Debt. Rwanda accessed the PBG independently but MINECOFIN confirmed its commitment to SLL issuance by June 2027. AFD's Kenya experience positions it as the natural partner to contribute to the co-design of the framework and support the issuance process.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Framework review (SPO) and climate KPI design with MINECOFIN / MDA | 30 |
| SPT calibration and verification architecture | 30 |
| Market sounding support (investor engagement) | 5 |
| Legal and structuring advisory for issuance | 15 |
| Total indicative TA | 80 |

FEASIBILITY SCORING

| Legal mandate | 3 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Framework review completed; climate KPI co-designed with MINECOFIN and MDA. | SLL/SLB issued (target: June 2027); verification framework in place; first SPT monitoring cycle launched. | N/A |

KEY RISKS

MINECOFIN issuance timeline slippage (June 2027 not legally binding)

Market conditions

Independent verification capacity in Rwanda

| ▸ Data Infrastructure |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| B1.2 | National deforestation monitoring as climate finance data infrastructure |  |
| Institution(s): REMA; Rwanda Forestry Authority; MINECOFIN — DG Debt (downstream user) |  | Year: Year 2–3 |  |

DLI DESCRIPTION

The Rwanda Forestry Authority and REMA operationalise a national deforestation and forest cover monitoring system producing annual, finance-grade data using a standardised and independently reviewed methodology compatible with SLF KPI requirements, voluntary carbon market standards, and REDD+ reporting frameworks, with data publicly accessible.

RATIONALE

Rwanda's NDC 3.0 includes forestry targets but no centralised, finance-grade deforestation monitoring system exists. The IMF Article IV 2025 flagged climate data infrastructure as a binding constraint. This data layer is the prerequisite for the forestry KPI in B1.3, but also serves voluntary carbon markets (actively explored by RSE and the government) and REDD+ registration. REMA and the RFA have the mandate but lack the methodology and capacity.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| MRV methodology design and peer review | 40 |
| Baseline deforestation dataset production support | 30 |
| REMA / RFA institutional capacity building | 20 |
| Linkage to capital market standards (ICMA, VCS, REDD+) | 5 |
| Total indicative TA | 95 |

FEASIBILITY SCORING

| Legal mandate | 3 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 3 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| MRV methodology designed; REMA/RFA capacity assessment completed. | Baseline dataset produced; annual monitoring cycle launched; REDD+ registration initiated. | Annual data published and data quality completed |

KEY RISKS

REMA / RFA technical capacity gaps

Satellite data access and processing costs

Methodology alignment with REDD+ / UNFCCC requirements

| ▸ Strategy & Framework |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| B1.3 | Forestry-anchored SLF framework and first issuance |  |
| Institution(s): MINECOFIN — DG Debt; REMA (KPI verification) |  | Year: Year 3 |  |

DLI DESCRIPTION

MINECOFIN develops and operationalises a Sustainability-Linked Finance framework anchored on Rwanda's nationally monitored deforestation and forest cover restoration KPIs (produced under B1.2), with AFD providing structuring TA and (potentially) co-financing the first issuance.

RATIONALE

This is AFD's differentiated positioning in Rwanda's sovereign debt landscape: no other donor is structuring a forestry-linked instrument. The instrument draws directly on the strong SLF experience in Rwanda (B1.1.) and deforestation data (B1.2) and aligns with a potential future AFD sovereign SLL to Rwanda. Conditioned on meaningful progress in B1.2.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Forestry KPI architecture and SPT calibration | 30 |
| SLF framework structuring and legal design | 10 |
| First issuance support (market sounding, investor engagement) | 10 |
| Peer exchange with Kenya SLF team | 5 |
| Total indicative TA | 55 |

FEASIBILITY SCORING

| Legal mandate | 3 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 5 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| N/A - Conditioned on B1.2 progress; framework scoping initiated. | Draft Forestry KPI framework co-designed. | First SLF issuance under forestry framework completed. |

KEY RISKS

Conditioned on B1.2 data availability

Ambitious timeline for a second-generation instrument

Issuer/Investor appetite for forestry-linked sovereign SLF in Rwanda

B2 — Financial Instruments: Insurance

Sub-objective:  Climate insurance products are accessible to Rwandan smallholders through the SACCO network, supported by a fit-for-purpose regulatory and market infrastructure.

The three DLIs under this sub-axis follow a strict regulatory-to-market sequence. B2.1 is the non-negotiable prerequisite: no climate insurance product can reach scale through SACCOs without a regulatory framework that authorises this distribution channel. It is also the most immediately achievable DLI in the cluster, with strong institutional ownership at BNR. B2.2 addresses the market structure constraint — individual insurer capacity is too thin for systemic climate risk — and is conditioned on regulatory clarity from B2.1. B2.3 is the market outcome: the first parametric product in active distribution, turning the infrastructure built under B2.1 and B2.2 into tangible access for smallholders. It is classified as a secondary strategic ambition given its full dependency on both upstream DLIs.

| ▸ Strategy & Framework |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| B2.1 |  | Regulatory framework for climate insurance distribution via SACCOs |  |
| Institution(s): BNR — Insurance Supervision; MINECOFIN; SACCO ecosystem |  | Year: Year 1 (prerequisite) |  |

DLI DESCRIPTION

BNR issues a regulatory framework authorising and standardising the distribution of parametric climate insurance products through the SACCO network, aligned with the National Insurance Strategy and the National DRF Strategy.

RATIONALE

SACCOs are the natural last-mile channel for smallholder climate insurance; the current regulatory architecture is not adapted. This framework is the foundational prerequisite for B2.2 and B2.3. It builds on the WB-funded MSME Bridge Lending Window and the DRF Diagnostic / National DRF Strategy (GSFF-funded), which identify parametric products as the micro-level layer of Rwanda's risk-layering architecture.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Regulatory framework drafting and legal review | 20 |
| BNR insurance supervision capacity building | 15 |
| SACCO network operational readiness assessment | 10 |
| Alignment workshop with National Insurance Strategy | 5 |
| Total indicative TA | 50 |

FEASIBILITY SCORING

| Legal mandate | 4 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Regulatory framework drafted and circulated for consultation. | Framework gazetted; supervisory guidance issued. | First SACCO licensed for climate insurance distribution. |

KEY RISKS

SACCO provincial consolidation timeline

Supervisory capacity at BNR insurance directorate

Alignment with National Insurance Strategy revision

| ▸ Market Activation |  | SECONDARY |  |
| --- | --- | --- | --- |
| B2.2 | Rwandan insurer pool for climate risk underwriting |  |
| Institution(s): Rwandan insurers; BNR — Insurance Supervision |  | Year: Year 2–3 |  |

DLI DESCRIPTION

A Rwandan insurer pool is formally constituted as an industry coordination structure for the underwriting and distribution of climate insurance products to smallholders and SACCOs, with reinsurance arrangements in place.

RATIONALE

Rwanda's insurance market is small and individual underwriting capacity is insufficient for systemic climate risk. An industry pool model addresses this structural constraint. This DLI adds the market-structure dimension to the WB / GSFF financial mechanism and is conditioned on B2.1's regulatory clarity. No active donor is working on insurance pool architecture.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Legal structuring of the insurer pool | 15 |
| Reinsurance sourcing and negotiation support | 10 |
| International peer pool exchange | 5 |
| Capital adequacy and governance framework | 8 |
| Total indicative TA | 38 |

FEASIBILITY SCORING

| Legal mandate | 2 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 2 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Pool feasibility study completed; insurer consultations launched. | MOU signed by participating insurers; legal structure formed. | Pool operational with capital and reinsurance arrangements in place. |

KEY RISKS

Industry coordination and competing insurer interests

Reinsurance availability for Rwanda climate risk

Capital adequacy requirements

| ▸ Market Activation |  | SECONDARY |  |
| --- | --- | --- | --- |
| B2.3 | First parametric climate insurance product in active distribution |  |
| Institution(s): BNR — Insurance Supervision; BNR — FSDI; Insurer pool; SACCO network |  | Year: Year 3 |  |

DLI DESCRIPTION

A first parametric climate insurance product (drought / excess rain trigger) is designed, priced, approved by BNR, and in active distribution to at least one province's SACCO network with measurable take-up.

RATIONALE

Rwanda's smallholder agriculture — food crops and tea — is among the most climate-exposed sectors. No parametric product tailored to the SACCO distribution context exists at scale. The DRF Strategy identifies parametric products as the micro-level layer of Rwanda's risk architecture. B2.3 turns B2.1's regulatory framework and B2.2's insurer pool into market reality. Data infrastructure exists in nascent form; BNR's sandbox track provides an approval pathway. AFD's global experience in parametric agricultural insurance provides differentiated technical capacity for product design and actuarial support.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Product design and trigger calibration (drought / excess rain) | 15 |
| Actuarial review and pricing validation | 10 |
| Claims process design and operational testing | 10 |
| SACCO distribution network awareness campaign | 10 |
| Total indicative TA | 45 |

FEASIBILITY SCORING

| Legal mandate | 3 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 4 / 4 |
| Institutional ownership | 2 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Product design completed; pricing methodology validated. | BNR approval obtained; pilot launched in one province. | Active distribution in 3+ provinces with measurable take-up. |

KEY RISKS

Take-up rate uncertainty among smallholders

Pricing affordability for target population

Operational complexity of claims settlement

Sequencing dependency on B2.1 and B2.2

B3 — Financial Markets

Sub-objective:  Rwanda's capital markets offer credible green financial products supported by a robust certification infrastructure and finance-grade ESG data.

The two DLIs under this sub-axis target the institutional and data infrastructure that Rwanda's nascent green capital market requires to function credibly. B3.1 addresses the certification gap at CMA: without a functioning green product certification mechanism and local SPO capacity, issuers cannot access the green bond market credibly, even where investor appetite exists. B3.2 operationalises the ESG data hub at RSE — the data layer that makes issuer-level sustainability claims verifiable and comparable. B3.1 is the more immediately achievable, given CMA's explicit request and the clear mandate gap it fills; B3.2 is longer-horizon but a direct complement.

| ▸ Strategy & Framework |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| B3.1 | CMA green product certification mechanism and sustainability function |  |
| Institution(s): CMA |  | Year: Year 1–2 |  |

DLI DESCRIPTION

CMA establishes a dedicated sustainable finance function and operationalises a green / social / sustainability-linked bond certification mechanism aligned with the Rwanda green taxonomy, with a local SPO panel capacity in place.

RATIONALE

CMA's existing GSS+ guidelines are not owned by market actors. The lean team (20 staff, new CEO) explicitly asked for advisory on a dedicated sustainability function. Local SPO / verification capacity is a confirmed gap (flagged in BRD's issuance experience). RSE has identified 92 potential issuers. Multiple donors are active at CMA (LuxDev, GIZ, AfDB) but the certification mechanism and local SPO panel remain unoccupied.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| Certification SPO development aligned with Rwanda green taxonomy | 15 |
| Sustainability function governance setup and staffing support | 10 |
| Local SPO panel design and capacity building | 10 |
| Issuer engagement and first certification pipeline | 8 |
| Total indicative TA | 43 |

FEASIBILITY SCORING

| Legal mandate | 4 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 1 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Sustainability function established at CMA. | Certification process published; first local SPO regulation. | N/A |

KEY RISKS

Capacity constraints at lean CMA team

Crowded donor landscape (LuxDev, GIZ, AfDB, GGGI)

Market demand for certifications among Rwandan issuers

| ▸ Data Infrastructure |  | IMMEDIATE |  |
| --- | --- | --- | --- |
| B3.2 | ESG Data Hub — RSE Green Exchange Window uptake |  |
| Institution(s): RSE; Rwandan issuers |  | Year: Year 1–2 |  |

DLI DESCRIPTION

The RSE Green Exchange Window operates as a regional ESG data hub with all Rwandan issuers reporting through the ESG GPS platform, and a first cross-border listing or data-sharing arrangement signed.

RATIONALE

RSE launched the Green Exchange Window with a LuxStock partnership and the ESG GPS platform on 27 April 2026. Phase II adds the uptake dimension: issuer reporting and regional integration. ESG data is a binding gap flagged by IMF and this DLI provides a concrete remediation. LuxDev already supports the Green Exchange Window but AFD could add the issuer-side uptake and the regional EAC harmonisation dimension.

TECHNICAL ASSISTANCE (INDICATIVE)

| TA Activity | Est. Days |
| --- | --- |
| ESG data architecture and issuer onboarding programme | 15 |
| Regional MoU negotiations with EAC partner exchanges | 5 |
| Cross-border listing feasibility study | 8 |
| Total indicative TA | 28 |

FEASIBILITY SCORING

| Legal mandate | 2 / 4 |
| --- | --- |
| Policy alignment | 4 / 4 |
| Donor complementarity | 3 / 4 |
| Institutional ownership | 3 / 4 |
| Composite score |  |

YEAR-BY-YEAR TRAJECTORY

| FY 2026–27 | FY 2027–28 | FY 2028–29 |
| --- | --- | --- |
| Issuer onboarding programme launched; ESG data architecture in place. | All Rwandan issuers reporting through ESG GPS platform. | First cross-border listing or data-sharing arrangement signed. |

KEY RISKS

Issuer reporting capacity and data quality

Regional uptake by EAC peer exchanges

Coordination with LuxDev on Green Exchange Window